## Releases
Item # | App | App Owner | Must go together with | Hard date Y/N | Dev complete date | QA start date | QA end date | QA Priority | PROD date | QA Lead | QA Team | Effort (PM) | QA type | QA Location | Duration | Projects | JIRA | Status | PROD Release (history) | Application | RLC | SNOW Ticket | Packages(s) | Contact | QAP Link | Remarks | QA Dates | Pending Approvals | Package List
EC1 | NIM only | EC | [6 empty] | 2018-08-09 | [6 empty] | NIM Bounceback application – UDI Url change |  | PROD | 2018-08-09 | NIM only | 109578 | CHG1188847 | n/a | Sunny/ Gowtham | Need QAP link from QA | DEV change complete- changes deployed in QA environment for testing | Awaiting confirmation from QA
EC2 | OOE/GTX/GUA | EC | [6 empty] | 2018-08-09 | [6 empty] | OOE/GTX/GUA Autosys jobs migration |  | PROD | 2018-08-09 | OOE/GTX/GUA | 112554 | CHG1201212 | n/a | Samir/Sergey Frizen |  |  | Changes are in QA ready
EC3 | OOE/GTX/GUA | EC | [6 empty] | 2018-08-09 | [6 empty] | OOE – Autosys Migration |  | PROD | 2018-08-09 | OOE/GTX/GUA | 111025 | CHG1195562 | n/a | Samir/Sergey Frizen | Need QAP link from QA | This is to migrate to new autosys version to run restart jobs, health check jobs and housekeeping jobs for OOE application | Changes are in QA ready
EC5 | OLT | EC | [6 empty] | 2018-08-09 | [6 empty] | Vestmark mutual fund sell all fix |  | PROD | 2018-08-09 | OLT | 110646 | CHG1193778 | PWFN031619 | Raghav /Diwakar | QAP-119950 | Vestmark QA | 07/25 QA Execution start |  | OLVP0470 SRK
VG6 | NIM | VG |  |  |  | No QA |  |  | 2018-08-11 | [6 empty] | GTM to LTM changes for GOM Access from NIM |  | PROD | 2018-08-11
EC18 | TPL | EC |  | Y |  |  |  |  | 2018-08-30 | Joe | 1 | 1 | Onshore | US |  | TPL Mark-up surveillance reports changes to reflect the updated Commission grid |  | QA | 2018-08-30 | TPL | 105922 | CHG1173897 | PWFN030854 | Robert V / Ella / Lev |  |  | QA |  | TPLBD505 SRD TPLBD531 SRD
EC7 | FIPS | EC | [6 empty] | 2018-08-16 | [6 empty] | GADL-4793 - Vestmark ID loss resulting in OET rejecting trades and trades late reporting GADL-3551 - PRR Missing stepout indicator for only rejected CMO/MBS product type Trade |  | PROD | 2018-08-16 | FIPS | 108108 89176 | CHG1182509 CHG1083844 | PWFN030318 20:00 - 22:00 | Antonio | QAP-81192 | QA testing. No additional testing required | L3 QA | Ruslan M. Grushko Eric Casimiro Jibu Koshy RM-CAB-WMA-IT-ClientFT-RetailTrading-T3 | FIBP1000 SRK FIBP1100 SRK FIBP1200 LCT FIBP1200 SRK FICP3100 SRK FICP3500 SRK FICP6300 LCT FICP6300 SRK FICP6700 LCT FICP6700 SRK FIPP3100 LCT FIPP3100 SRK FIPP3500 SRK FIUP4400 SRK
EC10 | FIPS | EC | [6 empty] | 2018-08-16 | [6 empty] | GADL-2950 Negative Yield issue for Municipal trades |  | PROD | 2018-08-16 | FIPS | 100112 | CHG1151095 | PWFN031253 | Antonio | QAP-48578 | Regression testing | L3 QA | Sreeni Gangavarapu Ruslan M. Grushko Craig Duncan (QAP) Eric Casimiro Jibu Koshy Michael Watral RM-CAB-WMA-IT-ClientFT-RetailTrading-T3 | FIUP3100 SRK
EC11 | OEN | EC | [6 empty] | 2018-08-16 | [6 empty] | GADL-5004 - To block incomplete Fixed income trades from being sent to Client Inquiry |  | PROD | 2018-08-16 | OEN | 111702 | CHG1198109 | PWFN031631 | Antonio | Need QAP link from QA | Regression testing for Fixed Income all products. Changes deployed in QA for testing | L3 7/23/2018
EC14 | OLT | EC | [6 empty] | 2018-08-16 | [6 empty] | DORs Decommissioning Revise mainframe components to no longer reference DORs components that are to be decommissioned |  | PROD | 2018-08-16 | OLT | 111527 | CHG1197390 | PWFN031256 | Mark | need QAP- | Regression testing | OLP – Equities regression test |  | OLPP1010 SRK OLPP2080 OLPP2090 OLPP2200
EC9 | TPLS Batch | EC | [6 empty] | 2018-08-17 | [6 empty] | GADL-4695 TPL job (TPLD000P) should not stop processing TPL MQ messages when there are pending transactions in the MQ queue |  | PROD | 2018-08-17 | TPLS Batch | 97516 | CHG1143309 | PWFN031423 | Antonio |  | No testing required | L3 QA |  | TPLD00AP CTC TPLD00AP JCL
EC12 | OLT | EC | [6 empty] | 2018-08-17 | [6 empty] | One Time job to run after PWFN031582 is installed for Bookkeeping. Create flat file with system names to be used as reference file for Bookkeeping. |  | PROD | 2018-08-17 | OLT | 112371 | CHG1200666 | one time job to run after PWFN031582 is installed | Viktoria | QAP-127679 | one time job to run after PWFN031582 is installed | 7/25/2018 ran in QA
EC13 | OLT | EC | [6 empty] | 2018-08-17 | [6 empty] | Create flat file with system names to be used as reference file for Bookkeeping. |  | PROD | 2018-08-17 | OLT | 112398 | CHG1200729 | PWFN031582 | Viktoria | QAP-127679 | This job will run on-demand if new system will be introduced | 2018-07-26 |  | OEWCASSV CPY OEWED11P JCL OEWED11P PRC OEWBD110 SRD
EC15 | OEN | EC | [6 empty] | 2018-08-23 | [6 empty] | Equity Preferred from OET to GOM,Julius,Eris |  | PROD | 2018-08-23 | OEN | 111111 | CHG1195766 | PWFN031609 | Arun Babita |  |  |  |  | OENP0180 SRK
SK1 |  | SK |  |  |  | No Formal QA. Only QAP required |  |  | 2018-08-30 | - | - | - | - | - |  | Volcker release to support UltraBond feed changes |  |  | 2018-08-30
SK2 | Volker | SK |  |  |  | No QA |  |  | 2018-08-30 | - | - | - | - | - |  | Volcker autosys migration |  |  | 2018-08-30
SK3 | RAVE | SK |  |  |  | No QA |  |  | 2018-08-30 | - | - | - | - | - |  | RAVE autosys migration |  |  | 2018-08-30
SK6 | Caesar | SK | [6 empty] | 2018-08-30 | Ketan |  |  | Offshore |  |  | Caesar August Release |  |  | 2018-08-30
VG4 | GBI COE NIM | VG | [6 empty] | 2018-08-31 | Artur | 1 | 0.25 | Offshore | Poland |  | Autosys migrations |  |  | 2018-08-31
VG7 | GBI,RJO, NIM | VG | [6 empty] | 2018-09-06 | Artur | 1 | 0.5 | Offshore | India |  | IAAS change, use new IP addresses |  |  | 2018-08-31
[9 empty] | ongoing | Artur/Ketan | 4 | 1 | Offshore | India |  | Buffer
[10 empty] | Artur | 1 | 1 | Offshore | Poland | Fidessa SOR | Fidessa SOR
2018-09-01
[9 empty] | 2018-09-06 | Artur | 2 | 2 | Offshore | India |  | GADL-4793 - Vestmark ID loss resulting in OET rejecting trades and trades late reporting - (CTB package PWFN030318) GADL-3551 - PRR Missing stepout indicator for only rejected CMO/MBS product type Trade | https://flow-jira.ubs.net/browse/TRADING-654 https://flow-jira.ubs.net/browse/TRADING-658 | QA | 09/06/2018 8/16/2018 | OET FIPS | 108108 | CHG1182509 | PWFN030318 | Robert V / Antonio Cua | QAP-81192 |  |  |  |  | Jayesh update
EC33 | OLT | EC | [6 empty] | 2018-09-07 | _NO-Testable | [5 empty] | Clone DORS VSAM file ODOR.V.D600 that may be used by non-DORs components. Run One Time job PWJC.RELEASE.CNTL(OLTE600P) to clone DORS file. New files will be OOLT.V.D600 | https://flow-jira.ubs.net/browse/TRADING-631 | QA | 2018-09-07 | OLT | 113394 | CHG1204802 |  | Mark | QAP-134002 | Testing by QA Team not required | Testing by QA Team not required |  | PWJC.RELEASE.CNTL(OLTE600P) | Mark update
EC29 | OLT | EC | [6 empty] | 2018-09-13 | Artur | 1 | 1 | Offshore | Poland |  | Revise mainframe components to no longer reference DORs components. -OLP components modified to reference cloned copybooks OLTC51CM & OLTCCMPL and cloned VSAM COLTD600 file | https://flow-jira.ubs.net/browse/TRADING-426 https://flow-jira.ubs.net/browse/TRADING-427 | QA | 09/13/2018 TBD 10/18/2018 08/09/2018 | OLT | 111527 | CHG1197390 | PWFN031256 PWFN031268 | Mark |  | Regression testing with other QA Teams OLP – COE Equities, ICST, OLS OLG – Vestmark QA Team | 7/19. We are targeting COE Frond end release since it has same scope for regression. |  | OLPP1010 SRK OLPP2080 SRK OLPP2090 SRK OLPP2200 SRK OLPP3100 SRK OLPP3101 SRK OLGP1010 OLGP2200 OLGP2201 OLGP3100 | Mark update
EC20 | OEN | EC | [6 empty] | 2018-09-13 | Joe | 1 | 1 | Offshore | India |  | Mark up project changes – new process to calculate Mark-up values and pass exec time information to confirms for ELN products | https://flow-jira.ubs.net/browse/TRADING-104 | Dev | 2018-09-13 | OEN | 105953 | CHG1173901 | PWFN031567 PWFN031568 PWFN031583 PWFN031597 PWFN031585 PWFN031665 PWFN031648 PWFN031579 PWFN031584 PWFN030543 PWFN031651 PWFN031653 PWFN031654 PWFN031655 PWFN031652 | Robert V / Ella / Normina | QAP-117259 |  |  |  | OEFD340P PRC OEFB0220 SRD OEFB0340 SRD OERD315A CTC OERD315B CTC OERD315C CTC OERD315D CTC OERD315P JCL OERD315P PRC OERD320A CTC OERD320B CTC OERD320C CTC OERD320D CTC OERD320P JCL OERD320P PRC OERD325A CTC OERD325P JCL OERD608P PRC OERD611P PRC OERD326P JCL OEFDEQMP JCL OERCEQI1 CPY OERBD320 SRD OERBD605 SRD OERDD321 SRD FIPD700P PRC OETC00EI CPY OEIC0030 CPY OEIC0050 CPY OENP0771 SRK OENP1027 SRK OENP0088 SRK OEMP0310 SRK OEMP0315 SRK OEIP0024 SRK OEIP0231 SRK OEIP0030 SRK OEIP0250 SRK OEIP0000 SRK TDBP0000 SRK
|  | VG | [6 empty] | 2018-09-13 | Joe | 2 | 1 | Offshore | India |  | COE – EQI Markup and markdown project change |  | QA | 2018-09-13 | COE | 112928 | CHG1202495 |  | Gowtham Anantharamu |  |  | 7/30/2018-9/12/2018
VG3 | COE | VG |  |  |  | In QA |  |  | 2018-09-13 | Joe | 1 | 0.5 | Onshore | US |  | Mark up / down |  | QA | 2018-09-13 | [6 empty] | Duplicate?
[9 empty] | 2018-09-13 | Artur | 1 | 0.25 | Offshore | Poland |  | One Time job to copy SUNGARD FCA Accounts to new SUNGARD 2 connection | https://flow-jira.ubs.net/browse/TRADING-273 | QA | 2018-09-13 | AA25003 - AT14262 - OLT - ONLINE TRADING | 114577 | CHG1211556 | n/a | William
[9 empty] | 2018-09-13 | Artur | 1 | 0.25 | Offshore | Poland |  | WMFIX/GAP Short Sell LOC ID and LOC BRKR Validate required fields LOC-ID and LOC_BRKR for short shell orders coming from WMFIX/GAP | https://flow-jira.ubs.net/browse/TRADING-273 | QA | 09/13/2018 -09/14/2018 | OLT | 111336 | CHG1197194 | PWFN031512 PWFN031546 PWFN031551 | William |  |  | 2018-08-13 |  | COLTD600 CPY DORS51CM OEMCEQTY OLTCFIXO OLTC51CM TXNCEQTY OLGP1010 SRK OLGP2200 OLGP2201 OLGP3100 OLGP3700 OLPP2080 OLVP0690 OEMP0030
LZ3 | GAP | LZ |  | N |  |  |  |  | 2018-09-13 | Artur | 1 | 1 | Offshore | Poland |  | GAP Alternative Destinations Sungard 4.2 |  | Dev | 2018-09-13
LZ1 | ACE | LZ |  | N |  |  |  |  | 2018-09-13 | Artur | 4 | 1 | Offshore | India |  | ACE maintenance release Bug fixes Setup for RRP Fidessa and Blaze Need regression test |  | Dev | 2018-09-13
VG5 |  | VG |  |  |  | In QA |  |  | 2018-09-13 | Artur | 1 | 0.5 | Offshore | Poland |  | FCA - changes - Admin user |  | QA | 2018-09-13
VG16 | COE | VG | [6 empty] | 2018-09-13 | Artur | 1 | 0.25 | Offshore | India |  | Minor changes to EQI Client Onboarding screen |  |  | 2018-09-13
|  | EC | [6 empty] | 2018-09-13 | ? | [5 empty] | MQ PUT error due to the wrong MQ name | https://flow-jira.ubs.net/browse/TRADING-666 |  | 2018-09-13 |  |  |  | PWFN031734 | Vika
EC21 | FIPS | EC | [6 empty] | 2018-09-13 | Ketan | [5 empty] | GADL-4763 Apply Odd Lot Fees of $35 to only certain types of Auction Trades | https://flow-jira.ubs.net/browse/TRADING-665 | QA | 2018-09-13 | FIPS | 97176 | CHG1138616 | PWFN031417 | Antonio |  |  | L3 |  | FIBP0000 SRK FIGP0010 SRK
EC23 | OER Batch | EC | [6 empty] | 2018-09-14 | [6 empty] | GADL-4533 Create a new job OERD967P to report Daily MQ's activity every hour daily from 8 am EST to 17:00 EST, Mon through Friday and then also at 8:00 AM EST on Sat and Sun | https://flow-jira.ubs.net/browse/TRADING-657 | QA | 2018-09-14 | OER Batch |  |  | PWFN031295 | Antonio |  |  | L3 QA |  | OERD967P JCL OERD967P PRC
[9 empty] | 2018-09-14 | Ketan or Joe | [5 empty] | GADL-2950 Negative Yield issue for Municipal trades | https://flow-jira.ubs.net/browse/TRADING-655 |  | 2018-09-14 | FIPS |  | CHG1151095 |  | Robert V / Antonio Cua | [5 empty] | Jayesh update
[9 empty] | 2018-09-14 | Ketan or Joe | [5 empty] | GADL - 5004 - To block incomplete Fixed income trades from being sent to Client Inquiry | https://flow-jira.ubs.net/browse/TRADING-656 |  | 2018-09-14 | OET |  | CHG1159771 |  | Robert V / Antonio Cua | [5 empty] | Jayesh update
EC22 | OER Batch | EC | [6 empty] | 2018-09-14 | Ketan or Joe | [5 empty] | GADL-4692 Order Entry Platform, "BOE", should not appear as a source system as BOE has been de-commissioned | https://flow-jira.ubs.net/browse/TRADING-659 | Dev | 09/14/2018 resched to November | OER Batch | 98219 | CHG1185126 | PWFN031412 | Antonio |  |  | L3 |  | OERBD055 SRD OERBD060 SRD
EC4 | FIPS | EC | [6 empty] | 2018-09-20 | Ketan or Joe | [5 empty] | GADL-4360 - An error in generating FIPS ID and assigning it to a Trade record in FIPS | https://flow-jira.ubs.net/browse/TRADING-660 | QA | 09/20/2018 08/09/2018 | FIPS | 105144 | CHG1170473 | PWFN031181 | Jayesh/Alex | QAP-86703 | Regression testing for Fixed Income all products required | L3 QA |  | FIPP8250 SRK
EC8 | TPS | EC | [6 empty] | 2018-09-21 | Artur | 1 | 0.5 | Offshore | Poland |  | CTPS Decommission Remove CTPS files from following jobs OERD200P TPSD005P TPSD010P TPSD110P TPSD120P | https://flow-jira.ubs.net/browse/TRADING-162 | QA | 09/21/2018 08/17/2018 | TPS | 111042 | CHG1195540 | PWFN031564 | Rochit/Satish | QAP-126549 | on-going QA testing.. Batch Reconciliation testing |  |  | OERD200P PRC TPSD005P PRC TPSD010P PRC TPSD110P PRC TPSD120P PRC
SK7 | Caesar | SK | [6 empty] | 2018-09-27 | Ketan | 8 | 1.5 | Offshore | Kiev |  | Caesar September Release |  |  | 2018-09-27
[10 empty] | Artur/Ketan | 2 | 1 | Offshore | India | Buffer | Buffer
[10 empty] | Artur | 2 | 1 | Offshore | Poland |  | Fidessa SOR | [7 empty] | Leo
2018-10-01
VG1 | COE | VG | [6 empty] | 2018-10-11 | Artur/Joe/Ketan | 4 | 1 | Offshore | India/Poland |  | Pop-up remediation for A3 |  |  | 2018-10-11
|  | EC | [6 empty] | 2018-10-18 | Artur | 2 | 1.5 | Offshore | India/Poland |  | Review and Release for C Share Purchase To address a gap in the C Share Positions BMSS report pertaining to 529 trades, enhance COE Review & Release process as follows: When a C share is being purchased in COE for a 529 account, evaluate the following: • Time horizon of the order = or > 4 years, regardless of aggregate household holdings If the above conditions is met, route the order for Review & Release. | https://flow-jira.ubs.net/browse/TRADING-403 |  | 2018-10-18 |  |  |  | PWFN031690 | Raghav / Anubhav |  |  | Sep 10 to Oct 5
[9 empty] | 2018-10-18 | ? | [5 empty] | GADL-5185 - Incorrect employee indicator based on account range | https://flow-jira.ubs.net/browse/TRADING-661 | QA | 2018-10-18 |  |  | CHG1211649 | PWFN031692 | Kovalyov, Leon / Dave, Jayesh | QAP-131237 | Pending completing of its regression testing in QA |  |  |  | Jayesh update
|  | EC | [6 empty] | 2018-10-18 | Joe | 2 | 2 | Offshore | India |  | NNM CD Block Redesign 1. Add eligibility block (71E) on OLT instead of NNM API 2. Elaborate the NNM API Return codes and assign new edits for each Scenario as per following table |  |  | October | TradeWeb OLT Message Broker | 106767 | CHG1176483 | PWFN031718 PWFN031719 PWFN031720 PWFN031621 PWFV029253 | Satish |  | QA has to provide the prod date. As of 8/29, it will be in October.
EC24 | OLT | EC | [6 empty] | 2018-10-18 | Artur | 1 | 1 | Offshore | India |  | Revise mainframe components to no longer reference DORs components. -OLK components modified to reference cloned copybooks OLTC51CM & OLTCCMPL, comment out unreferenced copybook CDORD600 -OLY component, comment out unreferenced copybook CDORD600 | https://flow-jira.ubs.net/browse/TRADING-423 https://flow-jira.ubs.net/browse/TRADING-421 | QA | 10/18/2018 TBD 09/20/2018 08/16/2018 | OLT | 111078 | CHG1195760 | PWFN031213 PWFN031240 | Mark | QAP-126549 | Regression testing | 7/19. We are targeting COE Frond end release since it has same scope for regression. OLY – PRCEF regression test OLK – MFP regression test |  | OLYP3100 SRK OLKP2200 SRK OLKP2201 SRK OLKP3100 SRK OLKP6010 SRK | Mark update
EC25 | TDB | EC | [6 empty] | 2018-10-25 | Artur | 2 | 1 | Offshore | India/Poland |  | Revise mainframe components to no longer reference DORs components. TDBP0111 -change to reference cloned map TDBM010 TDBP0118 -change to reference cloned map TDBM020 Screens were used for browsing MQs. But note screens no longer accessed. Options from Main Menu TDBX have changed such that Option 4, then 5 no longer goes to these screens. | https://flow-jira.ubs.net/browse/TRADING-424 | QA | 10/25/2018 TBD 9/20/2018 8/09/2018 | TDB | 104855 | CHG1169536 | PWFN031451 | Mark | QAP-126549 | Should be no QA testing but RTB said full regression? | 7/19. Screens no longer accessed as Main Menu functions changed |  | TDBM010 SRK TDBM020 SRK TDBP0111 SRK TDBP0118 SRK | Mark update
EC30 | SOF | EC | [6 empty] | 2018-10-25 | ??? | ??? | ??? | ??? | ??? |  | Revise mainframe components to no longer reference DORs components. -SOF component modified to reference cloned MQ input/output module SOFP1410 in place of DOSP1410 | https://flow-jira.ubs.net/browse/TRADING-429 | QA | 10/25/2018 TBD 10/18/2018 08/16/2018 | SOF | 104869 | CHG1169569 | PWFN031274 | Mark | QAP-126549 | Regression testing | 7/19. Provided EPAS team can QA test. |  | SOFP1410 SRk SOFP6100 SRK SOFP6300 SRK SOFP6400 SRK | Mark update
SK8 | Caesar | SK | [6 empty] | 2018-10-25 | Ketan | 8 | 1.5 | Offshore | Kiev |  | Caesar October Release |  |  | 2018-10-25
[10 empty] | Artur/Ketan | 2 | 1 | Offshore | India | Buffer | Buffer
[10 empty] | Artur | 2 | 1 | Offshore | Poland | Fidessa SOR | Fidessa SOR
2018-11-01
VG2 | NIM | VG | [6 empty] | 2018-11-08 | Artur | 3 | 1 | Offshore | Poland/India |  | Pop-up remediation for A3 |  |  | 2018-11-08
VG11 |  | VG |  |  |  | 2018-09-15 |  |  | 2018-11-08 | Joe | 2 | 1 | Offshore | India |  | [Project] iPreo - Phase 1 |  |  | 2018-11-08
LZ2 | ACE MF COE, OOE | LZ | VG8, EC? | N |  |  |  |  | 2018-11-08 | Artur | 8 | 1 | Offshore |  |  | CM major maintenance release |  |  | 2018-11-08
SK9 | Caesar | SK | [6 empty] | 2018-11-29 | Ketan | 8 | 1.5 | Offshore | Kiev |  | Caesar November Release |  |  | 2018-11-29
[10 empty] | Artur/Ketan | 4 | 1 | Offshore | India |  | Buffer
[10 empty] | Artur | 2 | 1 | Offshore | Poland | Fidessa SOR | Fidessa SOR
2018-12-01
VG9 | COE,OOE,NIM, etc. | VG | [6 empty] | 2018-12-06 | Artur | 4 | 1 | Offshore | India/Poland |  | [Project] ConsultWorks on Chrome |  |  | 2018-12-06
VG14 | VM MF | VG, EC |  |  |  | 2018-10-31 |  |  | 2018-12-06 | Artur | 1 | 0.25 | Offshore | India |  | [Project] VestMark - Options | https://flow-jira.ubs.net/browse/TRADING-30 | Dev | 2018-12-06
[10 empty] | Artur/Ketan | 4 | 1 | Offshore | India
[10 empty] | Artur | 2 | 1 | Offshore | Poland
[10 empty] | Ketan | 8 | 1.5 | Offshore | Kiev |  | CZR intermid testing
2019-01-01
VG8 | COE, OOE | VG | LZ2 |  |  | OCT |  |  | 2019-01-08 | Artur | [5 empty] | [Project] COE/Blaze - per Phone orders support for options |  |  | 2019-01-08
EC31 | TPS | EC | [6 empty] | 2019-01-10 | ? | [5 empty] | Revise mainframe components to no longer reference DORs components. -All online components changed to reference cloned abend handler program TPSP2400 in place of DORP2400 | https://flow-jira.ubs.net/browse/TRADING-431 | QA | 01/10/2019 08/16/2018 | TPS | 104864 | CHG1169547 | PWFN031397 | Mark | QAP-126549 | Regression testing | 7/19. QA tested by Frank Parodi or Mike Garda? Or ourselves according to Robert? |  | TPSSABND CPY TPSM240 SRK TPSP0300 TPSP0400 TPSP0600 TPSP0700 TPSP0800 TPSP0900 TPSP1100 TPSP1200 TPSP1201 TPSP2400 | Mark update
VG15 | COE | VG | [6 empty] | 2019-01-15 | Artur/Depan | [5 empty] | EBIX Phase 2 - Document capture/upload |  |  | 2019-01-15
EC26 | TDB | EC | [6 empty] | 2019-01-18 | ----- | - | - | - | - |  | Revise mainframe components to no longer reference DORs components. TDBDB80P -change to reference cloned ctrlcard TDBREUSE Note Job does not run in production. | https://flow-jira.ubs.net/browse/TRADING-425 | QA | 01/18/2019 08/10/2018 | TDB | 108092 | CHG1182497 | PWFN031528 | Mark | QAP-126549 | no QA testing. RTB says to delete job instead of making changes. |  |  | TDBDB80P PRC TDBREUSE CTC | Mark update
EC27 | TPS | EC | [6 empty] | 2019-01-18 | - | - | - | - | - |  | Revise mainframe components to no longer reference DORs components. 20 TPS IDCAM jobs, which backup VSAM files at EOD, modified to reference cloned control card TPSREPRO or TPSREPRE. 4 TPS source components modified to reference cloned copybook TPSOTALS. Executed by jobs for EOD reporting. | https://flow-jira.ubs.net/browse/TRADING-430 | QA | 01/18/2019 08/10/2018 | TPS | 108101 | CHG1182505 | PWFN031194 | Mark | QAP-126549 | no QA testing Cloning 2 control cards and 1 copybook. Changed 22 PRC and 5 SRD components accordingly. | 7/13. Batch |  | TPSD001P PRC TPSD123P TPSD315P TPSD351P TPSD355P TPSD356P TPSD358P TPSD558P TPSD640P TPSD940P TPSW400P TPSW401P TPSW402P TPSW403P TPSW404P TPSW405P TPSW406P TPSW407P TPSW408P TPSW409P TPSW410P TPSREPRE CTC TPSREPRO CTC TPSOTALS CPY TPSD0070 SRD TPSD0310 TPSD0311 TPSD0320 TPSM0320 | Mark update
2019-02-01
VG10 | COE | VG |  |  |  | 2018-11-15 |  |  | 2019-02-01 | [6 empty] | [Project] COE Allocations |  |  | 2019-02-01
EC32 | TAP | EC | [6 empty] | 2019-02-07 | [6 empty] | Revise mainframe components to no longer reference DORs components. -TAPP2500 online component changed to no longer transfer control to DORP0300 for DORS trades in 9 places. | https://flow-jira.ubs.net/browse/TRADING-432 | QA | 02/07/2019 08/16/2018 | TAP | 105282 | CHG1171057 | PWFN031545 | Mark | QAP-126549 | Regression testing | 7/19. QA tested by Frank Parodi or Mike Garda? Or ourselves according to Robert? |  | TAPP2500 SRK | Mark update
2019-03-01
VG12 |  | VG | [6 empty] | 2019-03-01 | [6 empty] | [Project] iPreo - Phase 2 |  |  | 2019-03-01
2019-08-01
VG13 | VM | VG |  |  |  | in Progress |  |  | 2019-08-31 | [6 empty] | VestMark Alpha - support for FIX allocations |  |  | 2019-08-31
TBD
| OOE | [7 empty] | TBD | [6 empty] | OOE - Autosys Migration |  | QA | rescheduled | OOE/GTX/GUA | 111025 | CHG1195562 | N/A | Samir/Sergey Frizen |  | This to migrate to new autosys version to run restart jobs, health check jobs and housekeeping jobs. | Ready in QA
EC16 | OLT | EC | [6 empty] | TBD | [6 empty] | NextShares - new rule set up |  | QA | TBD | OLT | N/A |  | N/A | Satish Ella |  | Place holder. Awaiting date from business
SK4 |  | SK | [6 empty] | TBD | [6 empty] | Volcker RSBPNL Project |  | Requirement Clarification | TBD
SK5 |  | SK | [6 empty] | TBD | [6 empty] | Volcker CDX Hedge Products |  | Requirement Clarification | TBD
LZ4 |  | LZ

## Sheet2
https://flow-jira.ubs.net/browse/QAP-
https://flow-jira.ubs.net/browse/SDLC-

## Estimations
Offshore | NFI | FI | Totall | Onshore | NFI | FI | Totall
Number of ppl in Area | 8 | 10 | 18 | Number of ppl in Area | 1 | 2 | 3
Time require | Artur's Project | Joe's Project | Ketan's Project | NFI Team | FI team
September Needed |  |  |  | 14.75 | 16.5
September Balance |  |  |  | -6.75 | -6.5
October Needed |  |  |  | 11 | 18
October Balance |  |  |  | -3 | -8
November Needed |  |  |  | 15 | 14
November Balance |  |  |  | -7 | -4
December Needed |  |  |  | 9 | 2
December Balance |  |  |  | -1 | 8

## Sheet3
| NFI | FI
Number of ppl in Area | 8 | 10
Time require | Artur's Project | Joe's Project | Ketan's Project | NFI Team | FI team
September Needed |  |  |  | 9 | 15.5
September Balance |  |  |  | -1 | -5.5
October Needed |  |  |  | 9 | 14.5
October Balance |  |  |  | -1 | -4.5
November Needed |  |  |  | 13.25 | 16
November Balance |  |  |  | -5.25 | -6
December Needed |  |  |  | 9 | 12
December Balance |  |  |  | -1 | -2